## Infrastructure
Age Friendly Implementation Plan Year One 1 April 2026 - 31 Mar 2027
Theme 1: Infrastructure
The built environment (including outdoor spaces, pavements, road crossings, parking, outdoor seating and accessible buildings) has an important impact on the mobility, independence and quality of life of people in later life
Strategic Aim | Action | Delivery Partners | Timeline When will it be done by? | How will you measure success? Key Performance Indicators | Outcome | RAG Status
Improving Public Spaces for Older People | To assess the accessibility of local venues for people with disabilities and older people, working in partnership with people with disabilities and older people to design and implement an Age and Access Friendly Charter | FODC SWAP Dementia NI | 2027-03-31 | Production of Charter co‑designed with older people and people with disabilities | A co‑designed Charter reflecting the priorities of older people and people with disabilities, ensuring it is relevant and widely supported
| 1.1 (b) To work with public sector partners and local businesses to improve the accessibility of local venues for older people and people with disabilities | FODC SWAP Dementia NI Alzheimers Society Local Businesses | 2027-03-31 | Promotion and development of Age and Access Charter across all FODC community, leisure and cultural services Number of FODC community, leisure and cultural service areas that have formally adopted and actively implemented the Age and Access Charter. | The Charter is actively promoted and embedded across all community, leisure and cultural services within FODC
| 1.1 (d) Identify new/future projects benefiting those with stability/mobility issues such as Footway Improvements including dropped kerbs | DFI and others | Gortin Road Improvements, Omagh, October 26 and Irvinestown Road Enniskillen, March 27. Provide Accessible Parking bays with dropped kerbs where criteria is satisfied | The inclusion of dropped kerbs at approriate road crossings. Provide a new footway at Maryville Terrace, Omagh where currently pedestrians walk on the busy road. Provide an improved footway with segregated pedestrian and cyclist paths on Irvinestown Road near the SWAH. Provide Accessible Parking bays on street locations where legislated. | Improved access for older peolple.
| 1.1 (e) Consider older pedestrians when assessing introduction of controlled crossings | DFI and others | Controlled Crossing, Drumquin. July 2026. Controlled Crossing Gortin Road, October 26. | Delivery of Controlled Crossings | Improved access for older people.
Support people to remain safely in their own homes for longer | 1.2 (a) Increase the level of adaptations to housing stock in the area for older people through grants system and adaptations to NIHE properties. Support new supported accommodation schemes and category 1 accommodation for older people (Category 1 Accommodation is specifically designed for active older people aged 55 and above who can live independently) | NIHE | Ongoing | Signposting to Grants office for welfare adaptation grants. Provison of adaptations to social housing eg showers, handrails and extensions. Support sheltered housing developments or housing for category 1's Number of social housing tenants in receipt of adaptations (e.g. level‑access showers, handrails, ramps, extensions). | Improved accessibility for older people through the area, provision of services to meet their needs.
| 1.2 (b) Deliver targeted communication to ensure older people, carers, and frontline staff are aware of agencies offering assistance with small household tasks | FODC SWAP | 2027-03-31 | Development and publication of an information sheet and online resource signposting people to agencies offering assistance with small household tasks Number of leaflets distributed | Older people are better supported with small household tasks through improved awareness of, and access to, agencies that can provide practical assistance
| 1.2 (c) Enable people to live safely in their homes through Home Safety and Fire Safety Checks | FODC NIFRS | Quarterly | Target of 200 people over 60 receiving Home Safety checks including referrals from the Stepping On Programme Number of referrals to NIFRS for Fire Safety checks for older people Number of Fire Safety checks completed following FODC referrals | Older people are more aware of all aspects of home safety, as well as specialist advice on topics such as heating and energy saving
Improving Transport for Older People | 1.3 (a) Promote smart passes, through various marketing initiatives with good news stories promoting services and easy to read timetables | Translink FODC PHA | 2026-03-31 | Completed: A summary of the Concession Pass application process was provided to a key contact within the Age Friendly Transport network. Using this information, they produced an Age Friendly–branded summary document incorporating the AFNNI logo, with the intention of distributing it to all Age Friendly Officers. In line with project delivery: A component of the Translink Accessibility Working Group focuses on passenger information and accessibility. The two Age Friendly–appointed transport representatives participate in this group, enabling them to receive regional updates and contribute to discussions. | Improve awareness of smart passes and increase of patronage on Public Transport
| 1.3 (b) Engage with decision makers to maintain transport services, improving the reliability, accessibility and affordability of transport within town, rural areas and hospital settings | Translink Community Transport FODC PHA WHSCT | 2027-03-31 | Local operational matters should be directed to the relevant Area Manager for bus services. At a regional level, Accessibility Management at Translink requested that Age Friendly nominate a primary point of contact to represent the interests of older passengers. Two representatives currently fulfil this role and have been invited to participate in all Translink Accessibility Working Group meetings alongside other key stakeholders. This arrangement provides an opportunity to gain an overview of Translink’s accessibility initiatives while also contributing suggestions and raising specific requests on behalf of senior users. Quarterly meetings of Fermanagh and Omagh Interagency Forum sub-group which includes community transport. Translink is represented on the Fermanagh and Omagh Sub-Regional Transport Plan Board, alongside DfI, DfC and the Council. The Transport Plan considers local transport issues and future needs and aims to address these through new policies and measures. These may include initiatives such as bus priority schemes and the development of new or enhanced public transport services and infrastructure. It is anticipated the draft Transport Plan will be issued for public consultation later this year which will provide an opportunity for additional engagement with other stakeholders including the Health Trust and other local transport providers. | Increased collaboration to review transport options and better integrated and cohesive infrastructure for increased accessibility, equality and safety.

## Participation & Access
Age Friendly Implementation Plan Year One 1 April 2026 - 31 Mar 2027
Theme 2: Participation and Access
Providing accessible activities and programmes is key to enabling older people participate in community life and feel connected
Strategic Aim | Action How will it actually be done | Delivery Partners | Timeline When will it be done by? | How will you measure success? Key Performance Indicators | Outcome | RAG Status
Increasing access through locally based delivery | 2.1 (a) Co-ordinate an annual Age Friendly activity programme of delivery in local communities | FODC SWAP | 2027-03-31 | Deliver activities throughout the year for older people, that reduce loneliness and build connections including Age Without Limits Day and Positive Ageing Month Publish and promote a Positive Ageing Month booklet both in print and online and distributed to at least 3,000 older people Establish baseline participation in older people's programmes, with a recorded baseline of 400 individuals attending during Year One Establish baseline participation of older people in community wellbeing programmes, with a recorded baseline of 1,000 individuals attending during Year One
| 2.1 (b) Promotion of grant aid opportunities to help community groups provide activities for older people as part of a district wide positive ageing approach | FODC SWAP WHSCT PHA | 2027-03-31 | Number of community groups reached through the promotion of grant aid opportunities to support activities for older people Number of Positve Ageing Month grants issued Number of FODC grants for Older Persons' Groups issued Establish baseline of 96 community groups as grant aid recipients during Year One | Older people across the district have better access to community activities and support through the awarding of grants that promote wellbeing, social connection, and positive ageing
| 2.1 (c) Work in partnership to support shops and businesses to be Age Friendly through an Age and Access Charter, Jam card training and supporting older people who wish to continue working | FODC | 2027-03-31 | Keep Fermanagh and Omagh District Council signed up to the Age‑Friendly Employer Pledge and continue taking actions that support an age‑inclusive workplace | Staff of all ages are valued, supported, and able to contribute effectively
Improving access to public and transport community transport | 2.2 (a) Work with Translink and Community Transport to support older people access to services and activities | FODC SWAP Translink Community Tranpsort | 2027-03-31 | At a regional level, Accessibility Management at Translink requested that Age Friendly nominate a primary point of contact to represent the interests of older passengers. Two representatives currently fulfil this role and have been invited to participate in all Translink Accessibility Working Group meetings alongside other key stakeholders. This arrangement provides an opportunity to gain an overview of Translink’s accessibility initiatives while also contributing suggestions and raising specific requests on behalf of senior users. | Increased collaboration to review transport options and better integrated and cohesive infrastructure for increased accessibility, equality and safety.

## Tackling Isolation
Age Friendly Implementation Plan Year One 1 April 2026 - 31 Mar 2027
Theme 3: Tackling Isolation
An Age Friendly community enables people of all backgrounds to actively participate and treats everyone with respect, regardless of age and supports actions to build respect and promote opportunities for inclusion by older people.
Strategic Aim | Action How will it actually be done | Delivery Partners | Timeline When will it be done by? | How will you measure success? Key Performance Indicators | Outcome | RAG Status
Building inclusion by older people at group and individual level | 3.1 (a) Capacity building to sustain the sector, including SWAP Cluster meetings and focus groups Develop an Older People's Forum for the district | SWAP FODC | Quarterly | Facilitate at least seven SWAP Cluster meetings bi-annnually. Quarterly meetings of Older Person's Forum. Liaise with members of Older People's Forum to devise a Communications Strategy | Provide structured opportunities for older people to share their views and influence local priorities
| 3.1 (b) Work with the Policing and Community Safety Partnership on safety programmes tailored for older people | FODC PCSP PSNI | 2027-03-31 | Delivery of a road safety session for older drivers Delivery of two scam awareness and home safety awareness sessions | Older people have increased awareness of road safety and scam prevention
| 3.1 (c) Promote volunteer recruitment and recognise volunteers | FODC Volunteer Centres | 2027-03-31 | Promotion of Volunteer Recognition Week Commitment to encourage more older people to become volunteers | Increased awareness and recognition of value that older people bring to the district through volunteering.
| 3.1 (d) Promote scam awareness, tailored for older people Crime Prevention Officer delivers talks and engagement sessions to older people's groups Focus on scams, burgarly prevention, personal safety and fraud awareness | PSNI PCSP SWAP Assist NI Community Groups | 2027-03-31 | Deliver at least 20 crime prevention talks Number of engagement sessions delivered Verbal feedback from talks and engagement sessions | Older people feel more confident and empowered to protect themselves, with a clear understanding of how to report incidents and reassurance that seeking support is appropriate and encouraged
| 3.1 (e) Promote services and support for people living on their own | FODC SWAP | 2027-03-31 | Develop and publish an information sheet and online resource promoting key services and supports for people living alone and distribute to the community and voluntary sector through the Fermanagh and Omagh District Council Community Newsletter Liaise with Volunteer Centres to develop good neighbour initiatives and/or other stakeholders to promote and develop projects to tackle isolation and loneliness | Increased awarness of services available for older people living on their own
Ensuring information is accessible to all | 3.2 (a) Providing literature in printed form as well as digital Development of e-clinics and Go On sessions | FODC SWAP Libraries NI | 2027-03-31 | Provide Age Friendly information in both printed and digital formats throughout the year. Report on uptake of referalls to e-clinics and Go On sessions Promote and organise technology‑support sessions to older people | Older people can access information in the format that suits them best. Older people can gain digital skills to suit their needs

## Health and Wellbeing
Age Friendly Implementation Plan Year One 1 April 2026 - 31 Mar 2027
Theme 4: Health and Wellbeing
The theme recognises that access to and availability of services is crucial in maintaining health and independence among older people and supporting sustainable communities
Strategic Aim | Action How will it actually be done | Delivery Partners | Timeline When will it be done by? | How will you measure success? Key Performance Indicators | Outcome | RAG Status
Increase awareness of local health care and wellbeing provision / initiatives | 4.1 Provide information on the provision of local health care and wellbeing initiatives. | FODC WHSCT | 2027-03-31 | Development and publication of an information sheet and online resource providing information on local health care and wellbeing initiatives through a robust joint communications strategy. Produce and distribute a list of contact numbers in the case of emergencies for older people, available in print and digital formats, ensuring it reaches a minimum of 3,000 older people across the district by the end of the reporting year. | Increased awareness by older people of local health care and wellbeing initiatives
Dementia awareness | 4.2 Increase awareness of dementia support services in the district | FODC SWAP WHSCT Dementia NI Alzheimer's Society PSNI | 2027-03-31 | Development and publication of an information sheet and online resource to people living with dementia and their families to increase awareness of dementia support services Raise awareness of Herbert Protocol through targeted awareness campaign | People with dementia and their families are more aware of available support
Living Well | 4.4 Delivery of health and wellbeing, including physical activity and falls prevention for older people | FODC SWAP | 2027-03-31 | Number of physical and cognitive activity programmes run by Community and Wellbeing Team and SWAP | Older people experience improved health, increased physical activity, and reduced risk of falls through participation in targeted health and wellbeing programmes
Tackling poverty | 4.5 Support wider work to address poverty among older people to alleviate food and fuel poverty and encourage older people to take up pension credit | FODC SWAP Advice Centres | 2027-03-31 | Up to 30 older people receiving targeted food support Run an energy efficiency workshop quarterly Provide targeted communication to increase uptake of eligible benefits, including Pension Credit, and deliver related engagement activities during Talk Money Week Elected Members to continue to lobby on behalf of older people Support SWAP Liaison Group Members to become Age Friendly Champions | Older people experience better financial security through food support, energy workshops, and greater awareness of Pension Credit
Promote positive outcomes for older people | 4.6 (a) ) PSNI to support older people through early identification of vulnerability, safeguarding intervention, crime prevention activity, and partner-based support and sign posting Officers identify vulnerability during routine calls or engagement with older people (e.g. hoarding, isolation, abuse, neglect, scams, financial exploitation) Immediate safeguarding actions taken where required Non-urgent concerns are referred internally to the Vulnerability Support Team for follow-up. Vulnerability Support Team conducts follow-up contact or home visits for older people identified as vulnerable Joint visits with Crime Prevention Officer where appropriate Assessment of risks, needs, and protective factors Referrals and signposting to appropriate statutory and voluntary services | WHSCT PCSP NIFRS Voluntary and Community Sector PSNI Dementia NI | 2027-03-31 | Number of people supported by Vulnerability Support Team follow-up Qualitatative case studies demonstrating positive outcomes Develop procedures for early identification of vulnerability in special circumstances eg storms | Older people at risk are identified earlier and receive timely safeguarding with multi-agency,co-ordinated support, reducing harm, repeat victimisation and an escalation of vulnerability
| 4.6 (b) Early Frailty Intervention Project (EFIP) made up of community based professional staff established in cross border localities, to identify people living with (or at risk of developing) frailty earlier | WHSCT FODC | 31/03/2027 (Commence in May 2026 x 3 year project ) | The EFIP has four key pillars of implementation: Fraility Assessment , Fraility Screening , Fraility Education Programme and Hybrid community co-ordination sessions. In year 1 establish an Early Frailty Intervention Hub in Omagh Leisure Centre and Templemore Complex Derry. The teams will consist of two Nurses, a Physiotherapist and an Occupational Therapist to identify people living with/at risk of developing frailty earlier and jointly deliver early/preventative interventions within their local community to help slow down or reverse the process. Two community connectors will also support the teams in signposting and supporting individuals to community and voluntary services that are appropriate for their identified need. | Improved and increased access to information and advice. Early Identification of high risk patients. Improved health outcomes contributing to less 'frail' individuals.